## week1
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 4th March
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 4th March | 11:00:00 | 18:00:00 | 5 | Reading the requirement and notes of the project. | Understanding the requirement of the project for the first week | Prepare the first meeting with group.
Tuesday | 5th March | 14:00:00 | 21:00:00 | 7 | Discussion and brainstorm the project with team members. | Every team members need provide their idea about the projects. | Provide ideas and meeting record to supervisor
Wednesday | 6th March | 12:00:00 | pm 17:00:00 | 6 | Searching for technology frameworks and development language. | Understanding which language should I use. | Prepare to learn PHP, PHP framework and server building.
Thursday | 7th March | 12:00:00 | 20:00:00 | 8 | Start to learning PHP | PHP is necessary for building websites back end. | Continue working on learning PHP and PHP framework
Friday | 8th March | 8:00:00 | 12:00:00 | 4 | Keep learning PHP and prepare next meeting | PHP is necessary for building websites back end. | Have a basic knowledges for PHP and framework.
|  |  | Total | 30

## week2
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 11th March
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 11th March | 7:00:00 | 14:00:00 | 7 | Doing research about social media platforms and list them. | Our project will implement by the research feedback | Organising the research feedback and demonstrate them in meeting.
Tuesday | 12th March | 9:00:00 | 15:00:00 | 6 | Doing research about front-end framework and back-end framework | Our website will be developed by these framework. | The framework “Laravel” is been chosen.
Wednesday | 13th March | 17:00:00 | 23:00:00 | 5 | Setting the Laravel running environment | Project “UniMingle” will be developed in Laravel | Read Laravel offical document and learning Laravel syntax.
Thursday | 14th March | 12:00:00 | 10:00:00 | 8 | Keep learning Larave syntax | Project “UniMingle” will be developed in Laravel | Continue learning Laravel syntax.
Friday | 15th March | 13:00:00 | 21:00:00 | 8 | Start doing research about server building | Our project will be implemented as a website.server building is necessary. | Have a rough idea about server building.
|  |  | Total | 34

## week3
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 18th March
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 18th March | 11:00:00 | 18:00:00 | 7 | Building the back-end data model, including different functions. | User module need different functions | Building successfully
Tuesday | 19th March | 6:00:00 | 13:00:00 | 7 | Building register application programming interface | Use for third part to log in | Continue building register API.
Wednesday | 20th March | 12:00:00 | 17:00:00 | 5 | Continue building register application programming interface | Building API for third part to log in | Building register API and fix bug successfully
Thursday | 21st March | 14:00:00 | 21:00:00 | 7 | Building back-end specific function modules | Specific function mostly for the project further extension. | Organising the functional modules and demonstrate them in next meeting.
Friday | 22nd March | 15:00:00 | 21:00:00 | 6 | Building forms of page module | Login and signup are core function module in the project. | Building successfully.
|  |  | Total | 32

## week4
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 25th March
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 25th March | 13:00:00 | 19:00:00 | 6 | Back-end framework setting and learning | API configurations will use back-end framework | Record the API configuration details and explain it to team members.
Tuesday | 26th March | 11:00:00 | 17:00:00 | 6 | Learning how to connect front-end and back-end in user module | It fit to Login and signup function of user module. | Continue working on data transport between front-end and back-end
Wednesday | 27th March | 7:00:00 | 15:00:00 | 8 | Prepare the first milestone sketches and prepare the meeting. | Next meeting some ideas about milestones of the project. | Provide some ideas about time division，event division to team members.
Thursday | 28th March | 12:00 | 5:00 | 5 | Modify the first milestone sketches. | Next meeting some ideas about milestones of the project. | Provide a rough but completed sketches in next meeting.
Friday | 29th March | 12:00:00 | 19:00:00 | 8 | Prepare the presentation of first milestone. | The project will be explained in the presentation. | Prepare the presentation and practice with team members.
|  |  | Total | 33

## week5
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 1st April
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 1st April | 18:00:00 | 23:00:00 | 5 | Continue on server building | Our project will be implemented as a website. A server is necessary. | Waiting for pop up online.
Tuesday | 2nd April | 10:00:00 | 16:00:00 | 6 | Server building and back-end development | Building the database environment is important for website development. | Pop the website up to internet.
Wednesday | 3rd April | 6:00:00 | 13:00:00 | 7 | Transport the user data to the front end | User module will collect data information and shows in the website. | Working on display bugs
Thursday | 4th April | 5:00:00 | 12:00:00 | 7 | Fix user page display bugs | User module transfer the data information but can not display it. | Fixed and recorded, demonstrate the record in next meeting.
Friday | 5th April | 12:00:00 | 17:00:00 | 5 | Building register functional modules | Register functional module is the essential part in user module. | Building successfully and pop up online
|  |  | Total | 30

## week6
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 1st April
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 1st April | 6:00:00 | 12:00:00 | 6 | Building back-end admin page | Our back-end server will manage event in admin page | Admin page building successfully and pop up online.
Tuesday | 2nd April | 10:00:00 | 17:00:00 | 7 | Building event module interaction, including event categories select. | Event categories and other functions is the essential part of event module | Continue working on event module, provide bug report to team members.
Wednesday | 3rd April | 7:00:00 | 12:00:00 | 5 | Working on fixing category bug of event module. | The bugs will incur categories that can not be chosen. | Now, user can select event categories as they want.
Thursday | 4th April | 5:00:00 | 12:00:00 | 7 | Building event creating page and learning tool “timer picker” | Use external plug-in tool “timer picker” to help user select event time | Building successfully, but “timer picker” does not work.
Friday | 5th April | 14:00:00 | 19:00:00 | 5 | Working on fixing time picker bug of event module. | User need “timer picker” to select event time and deadline time. | Fix successfully ,record and demonstrate in next meeting.
|  |  | Total | 30

## week7
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 1st April
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 29th April | 12:00:00 | 18:00:00 | 6 | Learning map API | A geography map will be included in UniMingle | Understand the usage of map API
Tuesday | 30th April | 12:00:00 | 18:00:00 | 6 | Try to integrate Google map API into UniMingle | A geography map will be included in UniMingle | Fail, need to analyze and understand deeper
Wednesday | 1st May | 14:00:00 | 18:00:00 | 4 | Discussing about map API with team members | A geography map will be included in UniMingle | Try to use team members' advices to debug
Thursday | 2nd May | 12:00:00 | 19:00:00 | 7 | Designing test cases for unit tests | Our website need to pass all tests before launch | Collect test results and discuss with others
Friday | 3rd May | 12:00:00 | 18:00:00 | 7 | Conducting units tests for back-end modules | To ensure there are not any bugs existing in back-end | Collect bugs and submit to GitHub
|  |  | Total | 30

## week8
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 1st April
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 6th May | 14:00:00 | 18:00:00 | 4 | Discussing with team members about testing plan | To decide which test will be conducted to test the whole website | Unit tests and performance tests are necessary
Tuesday | 7th May | 12:00:00 | 19:00:00 | 7 | Writing back-end code to implement admin functions | Our website need admin to manage both user module and event module | Finishing development, but need time to debug
Wednesday | 8th May | 10:00:00 | 15:00:00 | 5 | Bug fix in Google Map API integration | A geography map will be included in UniMingle, and it is the core function | Successfully integrate but need to test in various environments.
Thursday | 9th May | 12:00:00 | 19:00:00 | 8 | Testing white lists of Google Map API | To ensure that all users can get access to our heating map | Need further discussion and bug fixing
Friday | 10th May | 12:00:00 | 18:00:00 | 7 | Conducting tests on user module | To ensure user module can run well after adding new functions | New functions work well
|  |  | Total | 31

## week9
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 13th May
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 13th May | 13:00:00 | 18:00:00 | 5 | Discussing with team members about the milestone 2 | The milestone 2 is the most important milestone in this project | Had a rough outline of the milestone 2 report
Tuesday | 14th May | 12:00:00 | 19:00:00 | 7 | HTML responsive learning | Make sure our websites can be ran in the mobile end | Keep doing research about responsive.
Wednesday | 15th May | 10:00:00 | 18:00:00 | 8 | Conducting units tests on back-end codes | After each step develeopment, unit test should be conducted | Analyze test result and collect bug for fixing and debugging
Thursday | 16th May | 12:00:00 | 20:00:00 | 8 | Building interactive mechanism for event module | To improve the user experience of event module | Build successfully then pop up online
Friday | 17th May | 12:00:00 | 18:00:00 | 6 | Fixing bugs appeared when visting the homepage | Make sure the page is accessed properly | Fixing successfully
|  |  | Total | 34

## week10
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 20th May
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 20th May | 13:00:00 | 20:00:00 | 7 | Organizing all bugs met during tests so far | Bugs will be discuss and fixed with the help of all members | Discuss with team members
Tuesday | 21th May | 12:00:00 | 18:00:00 | 6 | Fixing bugs of Google Map API | Users need to visit the map page to join events | Temporary available, need to learn more
Wednesday | 22th May | 10:00:00 | 18:00:00 | 8 | Learning deeper in the aspect of Google Map API | Users need to visit the map page to join events so that a steady service is important | Optimize the codes of event module
Thursday | 23th May | 12:00:00 | 20:00:00 | 6 | Optimizing event module and map page | To improve user experience | Improve the jump efficiency of event module
Friday | 24th May | 12:00:00 | 18:00:00 | 6 | Optimizing Google Map API implementation on various browsers | Users may use different methods to visit our website | Users will have the same experience through various channels to visit UniMingle
|  |  | Total | 33

## week11
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 27th May
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 27th May | 12:00:00 | 16:00:00 | 4 | Discussing the poster design with group mates | Our project demonstration will use poster to show our work | Need to revise poster after discussion
Tuesday | 28th May | 12:00:00 | 19:00:00 | 7 | Searching for video demo materials | Our project demonstration will use video demo to show our work | Share materials with group mates and have discussion
Wednesday | 29th May | 10:00:00 | 18:00:00 | 8 | Conducting performance tests on users module | Performance tests can reflect the user experience of our website | Finish performance tests and collect bugs
Thursday | 30th May | 12:00:00 | 20:00:00 | 8 | Bug fixing to optimize the performance of user module | To ensure the normal operation of UniMingle | Finish debugging and pop up online
Friday | 31th May | 12:00:00 | 18:00:00 | 6 | Discussing with team members about video demo progress | Our project demonstration will use video demo to show our work | Decide outline of video demo
|  |  | Total | 33

## week12
MCI Project Weekly Time Sheet
Team | 15 | Student ID | A1693663 |  |  | Week starting: | 13th May
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 3th Jun | 13:00:00 | 18:00:00 | 5 | Prepare last final materials | Prepare all of document materials for the final due. | Upload all of document materials.
Tuesday | 4th Jun | 12:00:00 | 18:00:00 | 6 | Monitoring and maintaining backend database | Backend database determines the normal operation of our website | Collecting bugs and share with team members
Wednesday | 5th Jun | 13:00:00 | 20:00:00 | 7 | Prepare for the final presentation | Make sure the final presentation will be frequency | Practice more and improve skills
Thursday | 6th Jun | 15:00:00 | 20:00:00 | 5 | Check website last time to make sure there are no bugs | Make sure our websites can be ran successfully | Last time check, no bug
Friday | 7th Jun | 12:00:00 | 18:00:00 | 6 | Writng individual final report | Use individual final report to reflect the learning result | Submit final report
|  |  | Total | 29